## Task Register
ITERATION 2 ¦ TASK REGISTER
Diego Juarez: Project Leader • Update status and evidence after review or new commits
Task ID | Menu | Task / feature | Owner | Source file / function | Expected deliverable | Status | Evidence / open issue | Target date | Reviewer
T01 | 1 | Generate sensor readings | Diego Juarez | src/tasks_sim.cpp / generateSensorReadings() | Two readings from 100 cm; stored for reuse | Done | Manual test: option 1 saved identical readings used later | 2026-10-30 | Diego
T02 | 2 | Calculate fused estimate | Diego Juarez | src/tasks_sim.cpp / calculateFusedEstimate() | Weighted estimate from shared sample | Done | Manual test: options 1 to 2 matched readings | 2026-10-30 | Diego
T03 | 3 | Calculate estimation errors | Anthony Santana | src/evaluator.h/.cpp; src/tasks_eval.cpp / calculateEstimationErrors() | Absolute error comparison against truth | Done | Validated standard case: 3.12 / 0.07 / 2.16 cm | 2026-10-30 | Diego
T04 | 4 | Run low-noise scenario | Anthony Santana | src/tasks_eval.cpp / runLowNoiseScenario() | Low-noise sample and accuracy report | Done | Noise 0.5/1.0; validated saved-result display | 2026-10-30 | Diego
T05 | 5 | Run high-noise scenario | Anthony Santana | src/tasks_eval.cpp / runHighNoiseScenario() | High-noise sample and accuracy report | Done | Noise 8.0/15.0; validated saved-result display | 2026-10-30 | Diego
T06 | 6 | Run outlier scenario | Anthony Santana | src/tasks_eval.cpp / runOutlierScenario() | Fault sample; add +40 cm to Sensor 2 | Done | Outlier fused error 12.63 cm in observed run | 2026-10-30 | Diego
T07 | 7 | Display saved results | Anthony Santana | src/tasks_eval.cpp / displaySimulationResults() | Recent readings, weights, fusion, errors | Done | Option 7 redisplayed the same scenario data | 2026-10-30 | Diego
T08 | 0 | Switch-based menu and exit | Anthony Santana | src/main.cpp / main() | All seven menu tasks; exit and invalid-input handling | Done | C++17 build passed; menu/exit tested | 2026-10-30 | Diego
T09 | - | Shared-sample state integration | Anthony Santana; Diego review | src/simulation_state.h; src/tasks_sim.cpp; src/tasks_eval.cpp | Single LastSimulation state across options 1,2,3,7 | Done | Implemented and pushed; Diego review remains | 2026-10-30 | Diego
T10 | - | Class definitions and architecture diagram | Both | docs/System_Design_Report.pdf (report section) | Classes, private data/public methods, diagram | In Progress | Prepared in new report; teammate signoff pending | 2026-11-01 | Diego
T11 | - | Compile and manual testing | Anthony Santana; Diego reviews | g++ build; terminal test log / screenshots | Working build and scenario results | Done | Testing seen for all seven options; review pending | 2026-10-30 | Diego
T12 | - | Update README | Anthony Santana | README.md | Build/run instructions and menu details | In Progress | Draft ready; add to GitHub and review | 2026-11-01 | Diego
T13 | - | Revise project-plan Excel | Both | docs/Sensor_Fusion_Iteration2_Project_Plan.xlsx | Task table, timeline, contributions | In Progress | Draft workbook created; upload/review pending | 2026-11-01 | Diego
T14 | - | System-design PDF report | Both | docs/Sensor_Fusion_Iteration2_System_Design_Report.pdf | Architecture, classes, tasks, progress | In Progress | Draft PDF created; upload/review pending | 2026-11-01 | Diego
T15 | - | Pull request review and merge | Diego Juarez | GitHub PR feature/anthony-evaluation -> main | Reviewed and merged implementation | In Progress | Compare screen seen; approval/merge not verified | 2026-11-02 | Diego
T16 | - | Upload final repository documentation | Both | README.md; docs/ | README and both docs visible on main | Not Started | Need commit, push, merge, and verify main | 2026-11-02 | Diego
T17 | - | Individual Canvas submissions | Each member | Final GitHub repository link | One submitted repository link per student | Not Started | After final repository review | 2026-11-02 | Diego

## Overview
SENSOR-FUSION ¦ ITERATION 2 PLAN
Based on Iteration 1 PDF (October 13, 2026); updated with observed Iteration 2 implementation
Project | Owner | Technical lead | Iteration | Report date | Proposed final review | Repository
Sensor-Fusion System | Diego Juarez | Anthony Santana | 02 | 2026-10-30 | 2026-11-02 | Juarez-Diego-2007/sensor-fusion-simulation
Task status summary
Total tasks | Done | In progress | Not started
17 | 10 | 5 | 2
Current assessment
Code: compiled and ran all seven menu options; options 1, 2, 3, and 7 share the same saved sensor sample.
Project leader: Diego Juarez. Code review/merge and project status check-in still require confirmation.
Documents: updated PDF, Excel plan, and README prepared; upload them into GitHub before submission.
Timeline dates in this workbook reflect the original proposed plan where official due dates were not provided.
Review all claims with Diego, then confirm status of the final main branch and individual Canvas links.
Project purpose: simulate two noisy distance measurements, compute weighted fusion, and compare absolute errors against ground truth.

## Timeline
REVISED MILESTONE TIMELINE
Original proposed dates are kept where possible; dates are not official course deadlines
Milestone | Start | Target / end | Lead | Expected deliverable | Status | Notes
Scope and collaboration plan | 2026-10-13 | 2026-10-15 | Both | Iteration 1 plan and design decisions | Done | Original plan prepared October 13
Sensor and weighted fusion | 2026-10-16 | 2026-10-22 | Diego Juarez | Sensor and FusionEngine files | Done | Initial implementation reported completed in handoff
Evaluation, scenario tests and menu | 2026-10-23 | 2026-10-30 | Anthony Santana | Tasks 3-7 and main switch-based menu | Done | All options compiled and manually tested
Shared result integration | 2026-10-30 | 2026-10-30 | Anthony; Diego review | One sample for options 1,2,3,7 | Done | Pushed on Anthony branch; review pending
Excel, PDF and README | 2026-10-30 | 2026-11-01 | Both | Finished docs and readable README | In Progress | Drafts ready; commit to docs/ and review
PR merge, GitHub check and Canvas links | 2026-11-01 | 2026-11-02 | Both; Diego approval | Merged repository and individual links | Not Started | Nov 2 was proposed, verify actual instructor deadline

## Contributions
TEAM RESPONSIBILITIES & EVIDENCE
Record actual contributions; final peer-evaluation responses remain private
Member | Iteration 2 role | Implementation / contribution | Evidence | Still required | Review status
Diego Juarez | Project Leader; sensor and fusion lead | Initial Sensor class, FusionEngine and tasks 1-2. Coordinates daily progress, check-in, fair assignments, and tracker. | Diego handoff; existing source files and terminal outputs. | Review tasks_sim.cpp integration and PR; confirm final progress report. | Pending final approval
Anthony Santana | Evaluation, integration and menu lead | Evaluation class; error comparison; scenarios; menu; LastSimulation; integration; manual testing. | Terminal screenshots; feature/anthony-evaluation pushed commits. | Add README and docs, confirm final main branch, submit link. | Implementation verified
Both | Shared architecture and documentation | Design discussions; update report/Excel; repository readiness and individual submissions. | Iteration 1 plan, Iteration 2 report, updated task register. | Review actual dates, approve docs, finalize PR, each submit link. | In progress

## Testing
MANUAL TEST EVIDENCE
Observed examples from terminal screenshots; all readings in centimeters; other runs vary due to random noise
Scenario | Ground truth | Sensor 1 | Sensor 2 | Fused | S1 abs error | S2 abs error | Fusion abs error | Conclusion
Standard | 100 | 96.88 | 100.07 | 97.84 | 3.12 | 0.07 | 2.16 | Fusion better than Sensor 1, worse than Sensor 2
Low noise | 100 | 100.07 | 99.79 | 99.99 | 0.07 | 0.21 | 0.01 | Fusion better than both in this sample
High noise | 100 | 91.69 | 122.86 | 101.04 | 8.31 | 22.86 | 1.04 | Fusion better than both in this sample
Outlier | 100 | 99.77 | 142.64 | 112.63 | 0.23 | 42.64 | 12.63 | Healthy Sensor 1 beats fusion; faulty Sensor 2 degrades estimate
Manual verification sequence: 7 -> 1 -> 7 -> 2 -> 3 -> 7 -> 4 -> 7 -> 5 -> 7 -> 6 -> 7 -> 0
Validation: standard sample readings 96.88 and 100.07 gave fused 97.84; they matched across options 1, 2, 3, and 7.

## System Design
CLASSES, MENU & FILE DESIGN
Course requirement: each class lists private data/public methods; each task maps to exactly one menu entry
Type / component | Private data | Public interface / responsibilities | File(s) | Owner
Sensor | name, noiseLevel, weight, generator | constructor; generateReading(); getWeight(); getName() | sensor.h / sensor.cpp | Diego
FusionEngine | None | static weightedAverage(reading1,weight1,reading2,weight2) | fusion.h / fusion.cpp | Diego
Evaluation | sensor1Error, sensor2Error, fusedError | constructor; absoluteError(); printReport() | evaluator.h / evaluator.cpp | Anthony
LastSimulation (struct) | None (all public fields) | available, scenario, truth, readings, weights, fusedEstimate, fusedAvailable | simulation_state.h; instance in tasks_eval.cpp | Anthony
Flow: menu (main.cpp) -> tasks_sim.cpp / tasks_eval.cpp -> Sensor, FusionEngine, Evaluation -> LastSimulation -> console output